## Sheet1
MODULE | SUB MODULE | TIME PER SUB MODULE (DAYS) | TOTAL TIME (DAYS)
Grant Opportunity Identification | Search and filter | 4 | 8
| Custom Alerts | 4
Grant Application Preparation | Application Templates | 4 | 14
| Document Management | 5
| Collaboration Tools | 5
Application Submission Process | Submission Tracking | 5 | 11
| Electronic Submission | 4
| Deadline reminders | 2
Application Review and Tracking | Status Tracking | 5 | 11
| Reviewer Feedback | 4
| Historical Data and Analysis | 2
Reporting and Analysis | Pre-award reporting | 4 | 7
| Data visualization | 3
Integration with External Systems | Funding Database Integration (business central) | 4 | 7
| Data Export | 3
User Access and Permissions | Role Based Access Control | 3 | 6
| Audit Trail | 3
Deployment | staging(lauching to test server) | 1 | 12
| UAT | 10
| Production | 1
Post Deployment | Training of the core team | 2 | 28
| Quality Assurance and documentation | 10
| Handover | 1
| Training all the staff | 15
System Testing | Integration testing | 2 | 4
| Internal testing | 2